## Sayfa1
Task | Start Date | Days
Planning | 2017-10-18 | 6
Functional Specification Document | 2017-10-18 | 3
Work Analysis | 2017-10-21 | 2
Risk Analysis | 2017-10-23 | 1 | Analysis | Functional Specification Document | Work Analysis | Risk Analysis
Design | 2017-10-24 | 11
Design Specification Document | 2017-10-24 | 1 | Design | Design Specification Document | GUI Design | Map Design | Character Design | SFX Design
GUI Design | 2017-10-25 | 2
Map Design | 2017-10-27 | 2 | Development | Scripting | 3D Modelling
Character Design | 2017-10-29 | 3
SFX Design | 2017-11-01 | 3 | Testing | Gameplay Testing | Model Testing
Development | 2017-11-04 | 20
Scripting | 2017-11-04 | 10
3D Modelling | 2017-11-14 | 10
Testing | 2017-11-24 | 6
Gameplay Testing | 2017-11-24 | 2
Model Testing | 2017-11-26 | 4